## Sheet1
Task # | Target Date | No. Days | TASK | No. HOURS | Status
1 | 2014-02-04 | 16 | Borrowing/Transfer Module (vessel to vessel) | 64
Create new module wherein users can enter the vessel, the loaner vessel, the transaction date, transaction type (borrowed or transferred) and reason.
Transaction has two basis: un-issued (based on approved requisition) or already issued
User enters the items that are being borrowed
Approving officer approves the transaction
If transaction basis is on Requisition:
1. The system will modify/update the original "Intended To" of each borrowed items to a new "Intended To".
2. User has an option now to change "Intended to" on Issuance module and the system will validate if entered value is among the possible "intended to" values of the requisition.
2 | 2014-02-07 | 3 | Create vessel to vessel borrowing slip | 12
3 | 2014-02-12 | 3 | Create vessel to vessel transfer slip | 12
4 | 2014-02-18 | 4 | Create report for monitoring of borrowed or transferred items. | 16
5 | 2014-02-24 | 4 | Modify RS monitoring report | 16
Report should track usages of RS that are for stock
Report should also consider RS that were repurposed or borrowed
6 | 2014-03-12 | 12 | Modify requisition module | 48
The system should alert users if "Intended To" vessel has borrowed items.
The system should also closed borrowed transaction if RS is ALREADY ISSUED.
Add flag if RS is for immediate release (no more approval on Receiving and Issuance – upon pressing the Noted button status will automatically be approved) or for approval
Need to modify Receiving (RR) Module
Need to modify Issuance Module
–NOTE: BUT P.O STILL FOR APPROVAL.
7 | 2014-03-24 | 8 | Create warehouse transfer module | 32
Create new module wherein users can enter the origin warehouse, the destination warehouse, the transaction date, and the reason.
User enters the items that are being transferred
Approving officer approves the transaction
NOTE: The system should allow transferring of allocated items
8 | 2014-03-27 | 3 | Create warehouse to warehouse transfer slip | 12
9 | 2014-04-10 | 10 | Modify inventory reports | 40
10 | 2014-05-08 | 17 | Create Issuance report listing | 68
Create view and report for RS with stock
CREATES LEDGER OF ISSUANCES FOR RS FOR STOCK
Create report listing of RS for canvass
Additional Remarks column on RS
Modify Canvass module – add additional remarks on RS LOV
REPORT TO VIEW ALL WAREHOUSE ISSUE TRANSFER FROM MAIN TO PORT
OR PORT TO PORT IF ANY
REPORT OF ALL ITEMS BORROWED AND CORRESPONDING REPLACEMENT
TERMS OF PURCHASE ORDER CAN ADD OTHERS TERMS NOT ON THE REMARKS COL BUT ON TERMS OF PO
11 | 2014-05-22 | 10 | WMS interface modification | 40
call WMS barcode printing from Oracle RR module
Create RR with Confirmed QTY for uploading to WMS
WMS uploads RR to Oracle
WMS uploads Issuance to Oracle
ORACLE UPLOADS APPROVED ISSUANCE TO WMS FOR REPORT PRINTING AND CLOSING
Create Warehouse transfer list for uploading to WMS
WMS uploads Warehouse transfer to Oracle
12 | 2014-05-30 | 6 | Create RS monitoring page | 24
Should track RS items status whether RS items are already on PO, RR, or still on RS. Should also track if items are transferred or borrowed. User can go directly to the modules (PO, RR, ISSUANCE, Transfer, Borrowings) but with READ access only.
13 | 2014-06-05 | 4 | System should be able to send email notifications once RR is posted, the email address can be encoded on RS. | 16
14 | 2014-06-11 | 4 | Testing | 16
|  | 104 | TOTAL HOURS | 416